## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10702 | New | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. GO2223001538PH |  |  | ORD/000027/2022-2023 | 291/NKWSMD | 13/05/2022 | 09/11/2022 | PEMA BHUTIA | 100.81 | 0 | 0 | 85
Total | [13 empty] | 100.81 | 0 | 0