## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10703 | New | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P. BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000073/2022-2023 | 589/NKWSMD | 26/05/2022 | 22/03/2023 | M/S. ASHOK KUMAR PERIWAL | 277.69 | 252.26 | 90.84 | 100
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10703 | New | Left out scheme for Piped Water Supply Scheme form Bulbuley Jhora to Suruk Block-Kalimpong I, District Kalimpong in connection with Jal Jeevan Mission, under PHED DD-II GTA. |  |  | ORD/000006/2025-2026 | 489/NKWSMD | 09/04/2025 | 08/06/2025 | M/S. ASHOK KUMAR PERIWAL | 7.69 | 0 | 0 | 0
Total | [13 empty] | 285.38 | 252.26 | 88.39