## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10704 | New | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA AND ADJOINING AREA UNDER BHALUKHOP G.P. BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000218/2022-2023 | 1112/NKWSMD | 05/08/2022 | 23/03/2027 | SUNNY CONSTRUCTION | 327.77 | 300.53 | 91.69 | 100
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10704 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 25/12/2023 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | SM/10704 | New | Demand note for payment for Boundary pillars of the diverted forest land against proposed 0.0909 ha land to be diverted Jal Jeevan Mission. (Memo No. 549/9-57/441011, Dated, Kalimpong, the 20.03.2025) |  |  | BILL/00021/2025-2026 | 80/NK/C/W/FORES | 11/07/2025 | 11/07/2025 | DIVISIONAL FOREST OFFICER | 0.31 | 0 | 0 | 0
Total | [13 empty] | 333.54 | 300.53 | 90.1