## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 1552/NKWSMD | 19/10/2022 | 19/10/2022 | Resource Division | 0.89 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 1527/NKWSMD | 18/10/2022 | 18/10/2022 | Resource Division | 1.21 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | new connection |  |  | BILL/00021/2022-2023 | BP-2022-23-239 | 21/12/2022 | 21/12/2022 | WBSEDCL | 0.26 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | new connection |  |  | BILL/00022/2022-2023 | BP-2022-23-238 | 21/12/2022 | 21/12/2022 | WBSEDCL | 0.26 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 07/11/2023 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
7 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | PIPED WATER SUPPLY SCHEME FOR CHUNABHATTI BAZAR D.I.F & LISH FOREST UNDER KALIMPONG-I BLOCK, DISTRICT KALIMPONG, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PHE DTE. | Assistant Engineer II | Junior Engineer I | ORD/000074/2022-2023 | 590/NKWSMD | 26/05/2022 | 10/05/2025 | SRINIWAS AGARWAL | 112.55 | 0 | 0 | 100
8 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | SM/10729 | New | Supplementary Piped Water Supply Scheme for Chunabatti Bazar D.I.F & Lish Forest under Kalimpong-I Block District Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | Assistant Engineer II | Junior Engineer I | ORD/000279/2023-2024 | 156/NKWSMD | 30/01/2024 | 28/07/2024 | SRINIWAS AGARWAL | 20.6 | 0 | 0 | 100
Total | [13 empty] | 153.44 | 0 | 0