## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON | SM/10746 | New | PIPED WATER SUPPLY SCHEME FROM PAREN KHOLA TO RANGPO DIVISION UNDER SANGSEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer II | Junior Engineer III | ORD/000050/2022-2023 | 532/NKWSMD | 25/05/2022 | 21/11/2022 | YAMA CONSTRUCTIONS LLP | 190.09 | 0 | 0 | 100
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON | SM/10746 | New | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 1376/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 1.26 | 0 | 0 | 0
Total | [13 empty] | 191.35 | 0 | 0