## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM PHENTO SOURCE TO DUKA | SM/10748 | New | PIPED WATER SUPPLY SCHEME FROM PHENTO SOURCE TO DUKA UNDER KALIMPONG BLOCK-II, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000053/2022-2023 | 535/NKWSMD | 25/05/2022 | 21/11/2022 | SUNIL BAJLA | 155.54 | 32.83 | 21.11 | 96
Total | [13 empty] | 155.54 | 32.83 | 21.11