## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE | SM/10749 | New | PIPED WATER SUPPLY SCHEME FROM KHARKHOLA TO SADAR AND LOWER TOP LINE UNDER KALIMPONG GORUBATHAN BLOCK, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000038/2022-2023 | 503/NKWSMD | 25/05/2022 | 12/08/2024 | PRAYOG RAI | 102.55 | 97.81 | 95.38 | 100
Total | [13 empty] | 102.55 | 97.81 | 95.38