## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM BANGLA JHORA TO JOGITAR | SM/10750 | New | PIPED WATER SUPPLY SCHEME FROM BANGLA JHORA TO JOGITAR UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-I | ORD/000041/2022-2023 | 523/NKWSMD | 25/05/2022 | 24/07/2022 | M/S R.S. CONSTRUCTION | 48.43 | 12.32 | 25.44 | 0
Total | [13 empty] | 48.43 | 12.32 | 25.44