## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP | SM/10755 | New | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO LOWER DALEP UNDER BLOCK-II, KALIMPONG, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000052/2022-2023 | 534/NKWSMD | 25/05/2022 | 21/11/2022 | GETEN NAMGYAL BHUTIA | 199.1 | 90.5 | 45.45 | 65
Total | [13 empty] | 199.1 | 90.5 | 45.45