## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM KHARKHOLA TO LOWER REON | SM/10756 | New | PIPED WATER SUPPLY SCHEME FROM KHARKHOLA TO LOWER REON UNDER KALIMPONG BLOCK-I UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000054/2022-2023 | 536/NKWSMD | 25/05/2022 | 21/11/2022 | TIKARAM SHARMA | 101.69 | 24.38 | 23.98 | 90
Total | [13 empty] | 101.69 | 24.38 | 23.98