## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | SM/10787 | New | SURFACE WATER BASED NABGAON KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG WITHIN KALIMPONG DISTRICT UNDER BLOCK UNDER NEORAKHOLA W/S & Mtc DIVISION IN KALIMPONG DISTRICT. | Assistant Engineer II | Junior Engineer III | ORD/000186/2022-2023 | 961/NKWSMD | 12/07/2022 | 08/05/2023 | M/S KAMAK ENGINEERS AND CO. | 910.66 | 0 | 0 | 100
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | SM/10787 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | SM/10787 | New | ADDITIONAL WORK FOR SURFACE WATER BASED NABGAON KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KALIMPONG WITHIN KALIMPONG DISTRICT UNDER BLOCK UNDER NEORAKHOLA WATER SUPPLY AND MAINTENANCE DIVISION IN KALIMPONG DISTRICT. | Assistant Engineer II | Junior Engineer III | ORD/000122/2024-2025 | 2195/NKWSMD | 29/11/2024 | 28/01/2025 | RAMESH AGARWAL | 46.56 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | SM/10787 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer II ,Junior Engineer IV | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 974.9 | 0 | 0