## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | SURFACE WATER BASED NIMBONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | Assistant Engineer II | Junior Engineer IV | ORD/000188/2022-2023 | 963/NKWSMD | 12/07/2022 | 18/11/2024 | SRINIWAS AGARWAL | 677.16 | 572.53 | 84.55 | 85
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 15/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | Visit of National Jal Jeevan Mission Team to hills and with an aim to arrange logistical support. | Assistant Engineer II | Junior Engineer I | ORD/000223/2023-2024 | 1274/NKWSMD | 16/10/2023 | 15/11/2023 | YAMA CONSTRUCTIONS LLP | 11.22 | 11.22 | 100 | 100
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 20 | 100
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
7 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | Providing Piped Water Supply Scheme at Nimbong Khasmahal Zone (VII) Under Fourteen Village, Under Kalimpong Block-I & Kalimpong Block -II In the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division Public Health Engineering Directorate under 14 Village. (PART WORK ORDER) | Assistant Engineer II | Junior Engineer IV | ORD/000051/2025-2026 | 762/NKWSMD | 27/05/2025 | 25/08/2025 | DHANJIT TAMANG | 35.94 | 0 | 0 | 100
8 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | PROPOSED 0.0683 HA FOREST LAND TO BE DIVERTED FOR SURFACE WATER BASED NIMBONG KHAS MAHAL PWSS TO ACCOMMODATE FHTC |  |  | BILL/00279/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.32 | 0 | 0 | 0
Total | [13 empty] | 785.57 | 583.94 | 74.33