## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 13/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | Visit of National Jal Jeevan Mission Team to hills and with an aim to arrange logistical support. | Assistant Engineer II | Junior Engineer I | ORD/000223/2023-2024 | 1274/NKWSMD | 16/10/2023 | 15/11/2023 | YAMA CONSTRUCTIONS LLP | 11.22 | 5.61 | 50 | 100
4 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/10793 | New | SURFACE WATER BASED NIMBONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | Assistant Engineer II | Junior Engineer IV | ORD/000188/2022-2023 | 963/NKWSMD | 12/07/2022 | 08/05/2023 | SRINIWAS AGARWAL | 677.16 | 455.89 | 67.32 | 85
Total | [13 empty] | 759.95 | 461.5 | 60.73