## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME | SM/11312 | New | Piped Water Supply Scheme for Purba Kabi Gaon under Samthar G.P Kalimpong Block -I, Kalimpong Block-I, under Neorakhola W/S & Mtc Division, PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000135/2022-2023 | 815/NKWSMD | 30/06/2022 | 20/11/2023 | DIPENDRA CHETTRI | 96.46 | 66.22 | 68.64 | 95
Total | [13 empty] | 96.46 | 66.22 | 68.64