## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | SURFACE WATER BASED PARINGAR KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | Assistant Engineer I | Junior Engineer I,Junior Engineer II | ORD/000187/2022-2023 | 962/NKWSMD | 12/07/2022 | 22/02/2024 | THUPDEN BHUTIA | 757.27 | 630.04 | 83.2 | 90
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 15/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 | Assistant Engineer II | Junior Engineer I | ORD/000207/2023-2024 | 851/NKWSMD | 28/07/2023 | 28/11/2023 | THE ELECTRIC SPHERE | 0.87 | 0.39 | 45.21 | 90
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | (Continuation) Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months) | Assistant Engineer II | Junior Engineer I | ORD/000327/2023-2024 | 1458/NKWSMD | 30/11/2023 | 31/01/2024 | THE ELECTRIC SPHERE | 0.39 | 0.39 | 100 | 100
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer II | Junior Engineer IV | ORD/000268/2023-2024 | 1578/NKWSMD | 29/12/2023 | 08/01/2024 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.19 | 20 | 100
6 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 09/11/2023 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
7 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
8 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | Additional Surface Water Based Parinagar Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kalimpong-I Block within Kalimpong district under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. (TSM/010477) |  |  | ORD/000363/2025-2026 | 888/NKWSMD | 19/06/2025 | 17/09/2025 | BHUTIA AND SONS | 43.37 | 0 | 0 | 0
Total | [13 empty] | 851.36 | 631.02 | 74.12