## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer II | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 13/08/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | (Continuation) Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months) | Assistant Engineer II | Junior Engineer I | ORD/000327/2023-2024 | 1458/NKWSMD | 30/11/2023 | 29/01/2024 | THE ELECTRIC SPHERE | 0.39 | 0.39 | 100 | 100
6 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 | Assistant Engineer II | Junior Engineer I | ORD/000207/2023-2024 | 851/NKWSMD | 28/07/2023 | 25/11/2023 | THE ELECTRIC SPHERE | 0.87 | 0.19 | 21.7 | 90
7 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | SM/11313 | New | SURFACE WATER BASED PARINGAR KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | Assistant Engineer I | Junior Engineer I | ORD/000187/2022-2023 | 962/NKWSMD | 12/07/2022 | 08/05/2023 | THUPDEN BHUTIA | 757.27 | 447.48 | 59.09 | 90
Total | [13 empty] | 818.63 | 448.07 | 54.73