## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM DALDALEY JHORA TO PASSABONG | SM/11342 | New | PIPED WATER SUPPLY SCHEME FROM DALDALEY JHORA TO PASSABONG UNDER GITKOLBONG G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000128/2022-2023 | 808/NKWSMD | 30/06/2022 | 29/08/2022 | M/S. ASHOK KUMAR PERIWAL | 96 | 84.53 | 88.05 | 100
Total | [13 empty] | 96 | 84.53 | 88.05