## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR | SM/11354 | New | P.W.S SCHEME FROM HARESAY JHORA TO LOWER MUNSI DHURA AND KARBUTAR UNDER SANGSAY G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG. |  |  | ORD/000228/2022-2023 | 1357/NKWSMD | 21/09/2022 | 31/08/2024 | DINESH SHERPA | 135.69 | 126.58 | 93.28 | 95
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR | SM/11354 | New | Additional Work for Leftout Household in connection with Piped Water Supply Scheme from Harresey Jhora to Munsi Dhura and Karbutar Block- Kalimpong II, District Kalimpong in connection with JJM, under PHED DD-II GTA. |  |  | ORD/000373/2025-2026 | 867/NKWSMD | 16/06/2025 | 15/08/2025 | DINESH SHERPA | 6.66 | 0 | 0 | 0
Total | [13 empty] | 142.35 | 126.58 | 88.92