## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte | SM/11358 | School | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong | Assistant Engineer I | Junior Engineer IV | ORD/000151/2022-2023 | 930/NKWSMD | 12/07/2022 | 08/01/2023 | GETEN NAMGYAL BHUTIA | 177.33 | 126.23 | 71.18 | 80
Total | [13 empty] | 177.33 | 126.23 | 71.18