## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/11359 | School | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of School in Kalimpong Block-II in the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000154/2022-2023 | 931/NKWSMD | 12/07/2022 | 09/03/2023 | JUSTINE BHUTIA | 253.45 | 87.69 | 34.6 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/11359 | School | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/04/2024 TO 30/06/2024 (3 MONTHS). | Assistant Engineer I | Junior Engineer III | ORD/000291/2023-2024 | 706/NKWSMD | 27/03/2024 | 25/06/2024 | NIM TSHERING LEPCHA | 6.36 | 0 | 0 | 0
Total | [13 empty] | 259.81 | 87.69 | 33.75