## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 48 Nos of Aganwadi under Gorubathan Block, in the District of Kalimpong under Neorakhola water supply Division, kalimpong PHE Directorate. | SM/11363 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 48 Numbers of Aganwadi in Gorubathan Block under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer I | ORD/000157/2022-2023 | 934/NKWSMD | 12/07/2022 | 08/01/2023 | BHUTIA AND SONS | 232.03 | 215.85 | 93.03 | 95
Total | [13 empty] | 232.03 | 215.85 | 93.03