## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of Drinking water from spring water source for 13 Numbers Health care Facilities in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. | SM/11368 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for 13 Numbers of Health Care facilities in Kalimpong Block -I under the District of Kalimpong, under Neorakhola Water Supply & Maintenence Division, P.H.E Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer IV | ORD/000158/2022-2023 | 935/ NKWSMD | 12/07/2022 | 10/10/2022 | DIPESH RAI | 49.48 | 14 | 28.29 | 50
Total | [13 empty] | 49.48 | 14 | 28.29