## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Rongo Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte(Part1) |  | Junior Engineer I | ORD/000098/2022-2023 | 619/NKWSMD | 26/05/2022 | 25/06/2022 | BINOD TAMANG | 1.45 | 0.67 | 46.16 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Gorubathan I Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte |  | Junior Engineer I | ORD/000100/2022-2023 | 621/NKWSMD | 26/05/2022 | 25/06/2022 | TOPGAY BHUTIA | 3.84 | 2.39 | 62.23 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Rongo Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte(Part2) |  | Junior Engineer I | ORD/000097/2022-2023 | 618/NKWSMD | 26/05/2022 | 25/06/2022 | DORJEE SHERPA | 4.76 | 4.33 | 90.92 | 0
4 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Kumai Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division, Kalimpong PHE Dte |  | Junior Engineer I | ORD/000099/2022-2023 | 620/NKWSMD | 26/05/2022 | 25/06/2022 | DORJEE SHERPA | 4.85 | 4.52 | 93.16 | 0
5 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Samsing Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division, PHE Dte, Kalimpong |  | Junior Engineer I | ORD/000096/2022-2023 | 617/NKWSMD | 26/05/2022 | 25/06/2022 | BINOD TAMANG | 3.72 | 2.69 | 72.28 | 0
6 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Placement of 1 nos of site inspection vehicle at the disposal of SE-GTA Circle for inspection of JJM works (for the month of Nov 22 ) |  |  | BILL/00154/2023-2024 | BP-2023-24-112 | 17/07/2023 | 17/07/2023 | ORCHID TRAVELS | 0.4 | 0 | 0 | 0
7 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Placement of 1 nos of site inspection vehicle at the disposal of SE-GTA Circle for inspection of JJM works (for the month of DEC 22 ) |  |  | BILL/00155/2023-2024 | BP-2023-24-113 | 17/07/2023 | 17/07/2023 | ORCHID TRAVELS | 0.4 | 0 | 0 | 0
8 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  |  | BILL/00271/2023-2024 | BP-2023-24-191, | 26/09/2023 | 26/09/2023 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 3.3 | 0 | 0 | 0
9 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Placement of 1 nos of site inspection vehicle at the disposal of SE-GTA Circle for inspection of JJM works (for the month of JAN-23) |  |  | BILL/00156/2023-2024 | BP-2023-24-114 | 17/07/2023 | 17/07/2023 | ORCHID TRAVELS | 0.4 | 0 | 0 | 0
10 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Ahalay Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer I | ORD/000101/2022-2023 | 622/ NKWSMD | 26/05/2022 | 25/06/2022 | DORJEE SHERPA | 4.38 | 2.54 | 58.09 | 100
11 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Dalim Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division, Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer I | ORD/000102/2022-2023 | 623/ NKWSMD | 26/05/2022 | 25/06/2022 | BINOD TAMANG | 3.7 | 3.09 | 83.56 | 100
12 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for the period of 6 (Six) months. Note: With effect from date of issuing work order. |  |  | ORD/000394/2022-2023 | 2899/NKWSMD | 31/03/2023 | 30/09/2023 | S S CONSTRUCTIONS | 0.99 | 2.3 | 232.36 | 80
13 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  |  | BILL/00608/2023-2024 |  | 08/01/2024 | 08/01/2024 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 0.96 | 0 | 0 | 0
14 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  |  | BILL/00607/2023-2024 |  | 08/01/2024 | 08/01/2024 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 0.32 | 0 | 0 | 0
15 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | STATIONARY BILL FOR JJM |  |  | BILL/00609/2023-2024 |  | 08/01/2024 | 08/01/2024 | WEST BENGAL GENERAL SERVICE CO-OPERATIVE SOCIETY LTD. | 0.81 | 0 | 0 | 0
Total | [13 empty] | 34.28 | 22.54 | 65.74