## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 1371/NKWSMD | 22/09/2022 | 22/09/2022 | Resource Division | 0.91 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | new connection |  |  | BILL/00010/2023-2024 | BP-2023-24-6 | 25/04/2023 | 25/04/2023 | WBSEDCL | 0.26 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | PIPED WATER SUPPLY SCHEME FOR RIYONG FOREST & RIYANG RAILWAY STATION WATER SUPPLY SCHEME UNDER TISTA GRAM PANCHAYAT, KALIMPONG BLOCK-I, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG. | Assistant Engineer II | Junior Engineer IV | ORD/000183/2022-2023 | 927/NKWSMD | 12/07/2022 | 08/01/2023 | GREEN VALLEY CONSTRUCTION | 185.43 | 106.63 | 57.5 | 85
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.02.2024 to 31.03.2024. | Assistant Engineer II | Junior Engineer I | ORD/000319/2023-2024 | 168/NKWSMD | 31/01/2024 | 31/03/2024 | YAMA CONSTRUCTIONS LLP | 0.79 | 0.79 | 100 | 99
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.04.2024 to 31.05.2024. | Assistant Engineer II | Junior Engineer I | ORD/000322/2023-2024 | 718/NKWSMD | 29/03/2024 | 29/05/2024 | YAMA CONSTRUCTIONS LLP | 0.79 | 0.79 | 100 | 100
6 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate for the period from July 2024 to December 2024. | Assistant Engineer II,Assistant Engineer5 | Junior Engineer I,Sub-Assistant Engineer | ORD/000044/2024-2025 | 1205/NKWSMD | 10/07/2024 | 06/01/2025 | YAMA CONSTRUCTIONS LLP | 0.99 | 2.29 | 231.12 | 60
7 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11376 | New | Regarding quotation of new transformer at Riyong forest and Riyang Railway Station. |  |  | BILL/00161/2025-2026 |  | 07/08/2025 | 07/08/2025 | WBSEDCL | 6.24 | 0 | 0 | 0
Total | [13 empty] | 195.4 | 110.49 | 56.54