## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11377 | New | PIPED WATER SUPPLY SCHEME FOR SUNTALAY KHASMAHAL UNDER TISTA G.P., KALIMPONG BLOCK-I, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, P.H.E DIRECTORATE, KALIMPONG. | Assistant Engineer II | Junior Engineer III | ORD/000173/2022-2023 | 949/NKWSMD | 12/07/2022 | 26/06/2025 | M/S. ASHOK KUMAR PERIWAL | 86.51 | 46.2 | 53.4 | 56
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11377 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00812/2023-2024 | BP-2023-24-525 | 21/02/2024 | 21/02/2024 | WBSEDCL | 5.57 | 0 | 0 | 0
Total | [13 empty] | 92.09 | 46.2 | 50.17