## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11577 | New | SEPKHOLA PIPED WATER SUPPLY SCHEME UNDER MAZEOK FOREST VILLAGE, SAMTHAR G.P, Kalimpong Block-I, Under Neorakhola Water Supply & Maintainance Division, PHE Dte, Kalimpong. |  |  | ORD/000230/2022-2023 | 1444/NKWSMD | 28/09/2022 | 25/06/2023 | D AND B GRACE | 40.88 | 18.08 | 44.24 | 95
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11577 | New | Leftout Estimate for Piped Water Supply Scheme from under Mezeko Forest, Samthar G.P, Block:-Kalimpong-I P.S:- Kalimpong District:Kalimpong. |  |  | ORD/000138/2024-2025 | 2329/NKWSMD | 17/12/2024 | 15/02/2025 | D AND B GRACE | 5.88 | 0 | 0 | 0
Total | [13 empty] | 46.76 | 18.08 | 38.68