## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11577 | New | SEPKHOLA PIPED WATER SUPPLY SCHEME UNDER MAZEOK FOREST VILLAGE, SAMTHAR G.P, Kalimpong Block-I, Under Neorakhola Water Supply & Maintainance Division, PHE Dte, Kalimpong. |  |  | ORD/000230/2022-2023 | 1444/NKWSMD | 28/09/2022 | 26/06/2026 | D AND B GRACE | 40.88 | 18.08 | 44.24 | 95
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11577 | New | Leftout Estimate for Piped Water Supply Scheme from under Mezeko Forest, Samthar G.P, Block:-Kalimpong-I P.S:- Kalimpong District:Kalimpong. |  |  | ORD/000138/2024-2025 | 2329/NKWSMD | 17/12/2024 | 15/02/2025 | D AND B GRACE | 5.88 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11577 | New | Demand note for payment for Boundary pillars of the diverted forest land against the proposed diversion of 0.0241 hectares of forestland under Jal Jeevan Misison (JJM) scheme for proposed gravity based and pumping based piped water supply scheme Nazeok Forest Village, Samthar GP, Kalimpong Block -I, Kalimpong, West Bengal |  |  | BILL/00158/2025-2026 |  | 07/08/2025 | 07/08/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.77 | 0 | 0 | 0
Total | [13 empty] | 47.53 | 18.08 | 38.05