## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11578 | New | SURUK KHAS MAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTAHAR G.P, KALIMPONG BLOCK-I, UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE, KALIMPONG |  |  | BILL/00415/2024-2025 | BP-2024-25-341 | 01/10/2024 | 01/10/2024 | WBSEDCL | 4.86 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | SM/11578 | New | SURUK KHAS MAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTAHAR G.P, KALIMPONG BLOCK-I, UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE, KALIMPONG |  |  | ORD/000242/2022-2023 | 1496/NKWSMD | 14/10/2022 | 12/04/2023 | M/S. ASHOK KUMAR PERIWAL | 369.37 | 0 | 0 | 100
Total | [13 empty] | 374.22 | 0 | 0