## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAIL PROJECT REPORT OF LOWER DARA GAON AND UPPER & LOWER GAIRI GAON PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | SM/11579 | New | PWSS Scheme for Lower Dara & Upper Dara and Lower Gari Gaon including construction of Catchment, desilting tank, rising main, distribution network including construction of RCC tank and protection work for the pipe under Kalimpong Block-I under Kalimpong District under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. |  |  | ORD/000243/2022-2023 | 1497/NKWSMD | 14/10/2022 | 12/04/2023 | M/S. ASHOK KUMAR PERIWAL | 306.11 | 248.74 | 81.26 | 100
Total | [13 empty] | 306.11 | 248.74 | 81.26