## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT | SM/12180 | New | WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-I BLOCK, UNDER KALIMPONG DISTRICT (TSM/012581) |  |  | ORD/000250/2022-2023 | 1528/NKWSMD | 18/10/2022 | 07/10/2024 | SRINIWAS AGARWAL | 400.34 | 372.38 | 93.02 | 80
Total | [13 empty] | 400.34 | 372.38 | 93.02