## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK | SM/12181 | New | Additional FHTC estimate for the work Piped Water Supply Scheme from Khani Khola to West Samalbong SM Code 09669 / IMIS ID 40012989 |  |  | ORD/000217/2023-2024 | 1282/NKWSMD | 17/10/2023 | 16/11/2023 | BASANT PRADHAN | 4.64 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK | SM/12181 | New | WATER SUPPLY SCHEME FOR SINGI KHASAMAHAL PIPED WATER SUPPLY SCHEME IN KALIMPONG-I BLOCK UNDER KALIMPONG DISTRICT. |  |  | ORD/000258/2022-2023 | 1621/NKWSMD | 03/11/2022 | 31/01/2025 | SRINIWAS AGARWAL | 657.41 | 367.45 | 55.89 | 95
Total | [13 empty] | 662.05 | 367.45 | 55.5