## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/12629 | New | ELECTRO-MECHANICAL WORK FOR GRAVITY BASED AND PUMPING BASED P.W.S SCHEME FOR PEDONG KHASMAHAL(PART) UNDER PEDONG G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG |  |  | ORD/000271/2022-2023 | 1779/NKWSMD | 28/11/2022 | 27/01/2023 | THE ELECTRIC SPHERE | 19.28 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/12629 | New | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) ,work includes construvtion of Catchment chamber.Desilting tank. RCC Tank (Main Tank and Zonal Tank) ,Laying of gravity main HDPE PIPE, distribution HDPE pipe, and construction of Switch Room , boundary wall under 5 nos of zone inside the pedong Khasmahal under pedong Gram Panchayat , under Kalimpong Block -II , under Kalimpong district. |  |  | ORD/000237/2022-2023 | 1448/NKWSMD | 29/09/2022 | 26/07/2023 | SRINIWAS AGARWAL | 713.75 | 376.4 | 52.74 | 70
Total | [13 empty] | 733.03 | 376.4 | 51.35