## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/12630 | New | ELECTRO-MECHANICAL WORK FOR GRAVITY BASED AND PUMPING BASED P.W.S SCHEME FOR KASHONE KHASMAHAL UNDER KASHONE G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG. |  |  | ORD/000270/2022-2023 | 1778/NKWSMD | 28/11/2022 | 27/01/2023 | THE ELECTRIC SPHERE | 19.28 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/12630 | New | PROPOSED GRAVITY Based & Pumping Based piped water supply scheme, work includes construction of Catchment chamber. Desilting tank. RCC Tank (Main Tank and Zonal Tank) ,Laying of gravity main HDPE PIPE, distribution HDPE pipe, and construction of Switch Room , boundary wall under 5 nos of zone inside the Kashone Khasmahal under Kashone Gram Panchayat , under Kalimpong Block -II , under Kalimpong District. |  |  | ORD/000234/2022-2023 | 1450/NKWSMD | 29/09/2022 | 22/01/2024 | GARGO TRADERS | 869.52 | 227.53 | 26.17 | 70
Total | [13 empty] | 888.8 | 227.53 | 25.6