## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | SM/13602 | New | Material Requisition To Resource Division |  |  | RTOR000223/2022-2023 | 2601/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 2.74 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | SM/13602 | New | Material Requisition To Resource Division |  |  | RTOR000236/2022-2023 | 2711/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 2.74 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | SM/13602 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 09/11/2023 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | SM/13602 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | SM/13602 | New | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MONGPONG FOREST (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. |  |  | ORD/000290/2022-2023 | 2147/NKWSMD | 20/01/2023 | 19/07/2023 | SANTOSH TAMANG | 319.48 | 182.56 | 57.14 | 80
Total | [13 empty] | 341.81 | 182.56 | 53.41