## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 | New | SURFACE WATER BASED BONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | Assistant Engineer I | Junior Engineer III | ORD/000274/2022-2023 | 1876/NKWSMD | 14/12/2022 | 03/12/2024 | SRINIWAS AGARWAL | 534.86 | 480.59 | 89.85 | 100
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 | New | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 2029/NKWSMD | 29/12/2022 | 29/12/2022 | Resource Division | 6.25 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 | New | Logistic arrangement and hand holding support to Jalpaiguri Government Engineering College for conducting Geo-Technical investigation at GLR sites in different locations of Darjeeling & Kalimpong District under Jal Jeevan Mission. | Assistant Engineer II | Junior Engineer I | ORD/000244/2023-2024 | 137/AE-II/NKWSMD | 08/12/2023 | 08/02/2024 | YAMA CONSTRUCTIONS LLP | 6.99 | 0 | 0 | 100
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 | New | Material Requisition To Resource Division |  |  | RTOR000232/2022-2023 | 2586/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 6.25 | 0 | 0 | 0
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00809/2023-2024 | BP-2023-24-521 | 21/02/2024 | 21/02/2024 | WBSEDCL | 7.83 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | SM/13604 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00808/2023-2024 | BP-2023-24-520 | 21/02/2024 | 21/02/2024 | WBSEDCL | 5.66 | 0 | 0 | 0
Total | [13 empty] | 567.85 | 480.59 | 84.63