## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | PROPOSED GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. |  |  | ORD/000031/2023-2024 | 181/NKWSMD | 04/05/2023 | 03/05/2024 | MS. SURYA I PVT. LTD COMPANY | 393.31 | 52.69 | 13.4 | 70
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). |  |  | ORD/000380/2022-2023 | 75/AE-II/NKWSMD | 28/02/2023 | 10/03/2023 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). |  |  | ORD/000379/2022-2023 | 74/AE-II/NKWSMD | 28/02/2023 | 10/03/2023 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). |  |  | ORD/000381/2022-2023 | 76/AE-II/NKWSMD | 28/02/2023 | 10/03/2023 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0.95 | 100 | 100
5 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 249/NKWSMD | 12/05/2023 | 12/05/2023 | Resource Division | 6.1 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 25/12/2023 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0 | 0
7 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | SM/13605 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
Total | [13 empty] | 419.34 | 55.55 | 13.25