## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG | SM/13606 | New | PROPOSED SURFACE BASED PIPED WATER SUPPLY SCHEME FOR PUDDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. |  |  | ORD/000104/2023-2024 | 826/NKWSMD | 24/07/2023 | 16/09/2025 | M/S. ASHOK KUMAR PERIWAL | 345.67 | 0 | 0 | 90
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG | SM/13606 | New | Additional Work for Leftout household in connection with Proposed Gravity Based Piped Water Supply Scheme for Pudung Khasmahal Piped Water Supply Scheme under Kalimpong Block-I, District Kalimpong. |  |  | ORD/000374/2025-2026 | 875/NKWSMD | 17/06/2025 | 15/09/2025 | TIKARAM SHARMA | 72.6 | 0 | 0 | 0
Total | [13 empty] | 418.26 | 0 | 0