## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SURUK PIPED WATER SUPPLY SCHEME | SM/13607 | New | Material Requisition To Resource Division |  |  | RTOR000162/2022-2023 | 2620/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 2.08 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SURUK PIPED WATER SUPPLY SCHEME | SM/13607 | New | Material Requisition To Resource Division |  |  | RTOR000239/2022-2023 | 2713/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 2.08 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SURUK PIPED WATER SUPPLY SCHEME | SM/13607 | New | Water Supply Scheme For Suruk Under Jal Jeevan Mission In Gorubathan Block Under Kalimpong District, Under P.H.E Dte. |  |  | ORD/000310/2022-2023 | 2490/NKWSMD | 09/02/2023 | 09/02/2024 | M/S. ASHOK KUMAR PERIWAL | 636.52 | 0 | 0 | 60
Total | [13 empty] | 640.68 | 0 | 0