## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/13610 | New | Material Requisition To Resource Division |  |  | RTOR000222/2022-2023 | 2565/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.9 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/13610 | New | Creating Gravity Based Piped Water Supply For Today Ambeok Tea Garden Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. |  |  | ORD/000293/2022-2023 | 2151/NKWSMD | 20/01/2023 | 19/07/2023 | M/S R.S. CONSTRUCTION | 255.72 | 197.85 | 77.37 | 85
Total | [13 empty] | 257.62 | 197.85 | 76.8