## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/13611 | New | Material Requisition To Resource Division |  |  | RTOR000205/2022-2023 | 2553/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 2.36 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/13611 | New | Material Requisition To Resource Division |  |  | RTOR000237/2022-2023 | 2712/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 2.36 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/13611 | New | PIPED WATER SUPPLY SCHEME FOR SAMABIYONG TEA GARDEN UNDER JAL JEEVAN MISSION PROGRAMME. | Assistant Engineer-III | Junior Engineer-I | ORD/000313/2022-2023 | 2493/NKWSMD | 09/02/2023 | 09/02/2024 | M/S. ASHOK KUMAR PERIWAL | 640.39 | 440.8 | 68.83 | 90
Total | [13 empty] | 645.11 | 440.8 | 68.33