## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | Creating Gravity Based Water Supply Scheme for Kumai Forest Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. | Assistant Engineer I | Junior Engineer III | ORD/000055/2023-2024 | 416/NKWSMD | 05/06/2023 | 21/11/2025 | SACHIN RAI | 279.21 | 113 | 40.47 | 65
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 450/NKWSMD | 07/06/2023 | 07/06/2023 | Resource Division | 1.5 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 28/03/2024 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | PROPOSED 0.0826 HA LAND TO BE DIVERTED FOR KUMAI FOREST PIPED WATER SUPPLY SCHEME.(TSM/011843) |  |  | BILL/00278/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 2.86 | 0 | 0 | 0
Total | [13 empty] | 305.85 | 113 | 36.95