## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | SM/13613 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 367/NKWSMD | 29/05/2023 | 29/05/2023 | Resource Division | 1.87 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | SM/13613 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 23/08/2023 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | SM/13613 | New | PROPOSED 0.1128 HA LAND TO BE DIVERTED CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAMSING MIDDLE AND UPPER, UNDER BLOCK GORUBATHAN DISTRICT KALIMPONG. |  |  | BILL/00250/2025-2026 |  | 12/09/2025 | 12/09/2025 | DIVISIONAL FOREST OFFICER | 19.87 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | SM/13613 | New | PROPOSED 0.01468 HA LAND TO BE DIVERTED CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAMSING MIDDLE AND UPPER, UNDER BLOCK GORUBATHAN DISTRICT KALIMPONG |  |  | BILL/00289/2025-2026 |  | 24/09/2025 | 24/09/2025 | DIVISIONAL FOREST OFFICER | 4.49 | 0 | 0 | 0
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | SM/13613 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME, UNDER BLOCK:-GORUBATHAN. DISTRICT:-KALIMPONG, UNDER P.H.E Dte. | Assistant Engineer II | Junior Engineer I,Junior Engineer II | ORD/000044/2023-2024 | 358/NKWSMD | 26/05/2023 | 11/05/2025 | THUPDEN BHUTIA | 348.89 | 50.41 | 14.45 | 100
Total | [13 empty] | 383.52 | 50.41 | 13.14