## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13615 | New | Proposed Gravity Based Piped Water Supply Scheme For Lava Forest Under Lava Gitbeong G.P, Block : Kalimpong - II, District:Kalimpong | Assistant Engineer II | Junior Engineer III | ORD/000299/2022-2023 | 2350/NKWSMD | 01/02/2023 | 31/07/2023 | BHUTIA AND SONS | 93.5 | 54.28 | 58.05 | 100
2 | KALIMPONG | Kalimpong-II | Neorakhola W/S & Mtc.Div. | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13615 | New | Material Requisition To Resource Division |  |  | RTOR000206/2022-2023 | 2554/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.22 | 0 | 0 | 0
Total | [13 empty] | 93.71 | 54.28 | 57.92