## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13616 | New | Material Requisition To Resource Division |  |  | RTOR000199/2022-2023 | 2549/NKWSMD | 17/02/2023 |  | Resource Division | 0.76 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13616 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00663/2023-2024 | BP-2023-24-421 | 16/01/2024 |  | WBSEDCL | 1.83 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13616 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00663/2023-2024 | BP-2023-24-421 | 16/01/2024 |  | WBSEDCL | 1.83 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13616 | New | Proposed Pumping Based Piped Water Supply Scheme For Maria Khasmahal (Part) (Upper Rabek) Under Kagay G.P, Block : Kalimpong - II, District:Kalimpong | Assistant Engineer II | Junior Engineer III | ORD/000292/2022-2023 | 2149/NKWSMD | 20/01/2023 | 19/07/2023 | THUPDEN BHUTIA | 251.88 | 24.59 | 9.76 | 50
Total | [13 empty] | 256.3 | 24.59 | 9.59