## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 | New | Material Requisition To Resource Division |  |  | RTOR000227/2022-2023 | 2588/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.76 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 07/11/2023 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00513/2023-2024 | BP-2023-24-319 | 17/11/2023 | 17/11/2023 | WEST BENGAL PARIVESH CAMPA | 4.74 | 0 | 0 | 0
4 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 | New | Pumping Based Piped Water Supply Scheme for Turzam Forest under Teesta G.P. Block Kalimpong-I, District: Kalimpong. |  |  | ORD/000279/2022-2023 | 2005/NKWSMD | 23/12/2022 | 21/06/2023 | SANTOSH TAMANG | 221.13 | 0 | 0 | 50
5 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 | New | Pumping based Piped water supply scheme for Turzum Forest under Teesta G.P. Kalimpong Block- I District Kalimpong. |  |  | BILL/00095/2024-2025 | BP-2024-25-446 | 28/11/2024 | 28/11/2024 | WBSEDCL | 14.53 | 0 | 0 | 0
6 | KALIMPONG | Kalimpong-I | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | SM/13621 | New | Pumping Based Piped Water Supply Scheme for Turzum Forest under Teesta G.P. Block Kalimpong -I , District- Kalimpong. |  |  | BILL/00229/2024-2025 |  | 31/07/2024 | 31/07/2024 | WBSEDCL | 14.53 | 0 | 0 | 0
Total | [13 empty] | 261.75 | 0 | 0