## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | BINDU PIPED WATER SUPPLY SCHEME | SM/13622 | New | Material Requisition To Resource Division |  |  | RTOR000221/2022-2023 | 2600/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.07 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | BINDU PIPED WATER SUPPLY SCHEME | SM/13622 | New | Creating Gravity Based Piped Water Supply Scheme With Spring Water For Bindu Under Jal Jeevan Mission Under Gorubathan Block, District Kalimpong. Under P.H.E Dte. |  |  | ORD/000295/2022-2023 | 2153/NKWSMD | 20/01/2023 | 19/07/2023 | JOJO CONSTUCTION | 122.39 | 64.59 | 52.78 | 100
Total | [13 empty] | 123.46 | 64.59 | 52.32