## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | Material Requisition To Resource Division |  |  | RTOR000204/2022-2023 | 2552/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 4.08 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 2716/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 4.08 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAKAM FOREST UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. |  |  | ORD/000311/2022-2023 | 2491/NKWSMD | 09/02/2023 | 07/08/2024 | M/S. ASHOK KUMAR PERIWAL | 874.4 | 0 | 0 | 65
Total | [13 empty] | 882.57 | 0 | 0