## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAKAM FOREST UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. |  |  | ORD/000311/2022-2023 | 2491/NKWSMD | 09/02/2023 | 07/08/2024 | M/S. ASHOK KUMAR PERIWAL | 874.4 | 476.33 | 54.47 | 65
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | Material Requisition To Resource Division |  |  | RTOR000204/2022-2023 | 2552/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 4.08 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 2716/NKWSMD | 03/03/2023 | 03/03/2023 | Resource Division | 4.08 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | Demand note for payment for Boundary pillars of the diverted forest land against proposed 0.0559 ha land to be diverted Jal Jeeven Mission. (Memo No. 3666/9-57/441050, Dated, Kalimpong, the 12.12.2025) |  |  | BILL/00328/2025-2026 |  | 15/01/2026 | 15/01/2026 | WEST BENGAL STATE FOREST DEVLOPMENT AGENCY | 0.64 | 0 | 0 | 0
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | SM/13953 | New | Demand note for payment of Compensatory Afforestation (CA) and Net Present Value (NPV) against the proposed diversion of 0.0559 hectares of forestland under Jal Jeevan Mission (JJM) scheme for proposed gravity based and pumping based piped water supply scheme. (Memo No. 3667/9-57, Dated, Kalimpong, the 12.12.2025) |  |  | BILL/00329/2025-2026 |  | 15/01/2026 | 15/01/2026 | DIVISIONAL FOREST OFFICER | 2.86 | 0 | 0 | 0
Total | [13 empty] | 886.06 | 476.33 | 53.76