## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PANKHASARI KHASMAHAL PWSS | SM/14170 | New | Material Requisition To Resource Division |  |  | RTOR000200/2022-2023 | 2582/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 4.1 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PANKHASARI KHASMAHAL PWSS | SM/14170 | New | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR PANKHASARI KHASMAHAL PWSS (ZONE -1) to (ZONE-V) UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. | Assistant Engineer II | Junior Engineer III | ORD/000306/2022-2023 | 2470/NKWSMD | 06/02/2023 | 06/02/2024 | THUPDEN BHUTIA | 1193.6 | 980.9 | 82.18 | 80
Total | [13 empty] | 1197.7 | 980.9 | 81.9