## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | GORUBATHAN-I PWSS | SM/14172 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 772/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 11.19 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | GORUBATHAN-I PWSS | SM/14172 | New | GORUBATHAN KHASMAHAL PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG. |  |  | ORD/000092/2023-2024 | 716/NKWSMD | 18/07/2023 | 17/07/2024 | M/S R.S. CONSTRUCTION | 1121.37 | 0 | 0 | 15
Total | [13 empty] | 1132.56 | 0 | 0